## Project Requirements
ID | Functional Areas & Requirements
0 | General
0.1 |  | GUI: | Multiple, moveable, sizeable windows. Quick response
0.2 |  | Security: | Object-based. Password verification
0.3 |  | Roles: | System access determined in user validation
0.4 |  | Roles2: | All transactions labeled with user name, date, and time
0.5 |  | Single Entry: | Information must be entered only once and saved
0.6 |  | Input Validation: | Information validated on entry, detected errors must be resolved
0.7 |  | Input Validation 2: | List of possible data entries must be user maintained
0.8 |  | Name Entry: | Process hyphenated names
0.9 |  | Name Entry 2: | Allow name searches using standard wild card characters
0.1 |  | Modular: | Modular design to permit addition and replacement of capabilities
0.11 |  | Data Structure: | Capable of maintaining data for many users
0.12 |  | Data Strucure 2: | Includes one-to-many and one-to-one structures.
0.13 |  | Printing: | Possible to print any display with header information
0.14 |  | Reporting: | All printed reports can be viewed on workstation before printing
0.15 |  | Reporting 2: | Reports accessible as a whole or in parts
0.16 |  | Online Help: | Context sensitive and detatiled on-line help function to assist users.
0.17 |  | Online Help 2: | User updated
0.18 |  | Online Help 3: | Specific to each entry, inquiry module, screen and individual field while cursor is near
0.19 |  | Interface: | Menu driven with movement between pages without having to return to main menu
0.2 |  | Interface 2: | Standardized system messages
0.21 |  | Access: | Ability to access any screen with minimal sub-menuing
0.22 |  | Design: | Development accomplished using JAD methodology with immediate prototypes
0.23 | ? | Entry Sequence: | Unclear
0.24 |  | Error Message: | User notified if information entered out of sequence or missing requirements
0.25 |  | Error Message: | Notification includes reason for rejection and minimum requirements that must be met
0.26 |  | Key Data: | Failure to enter to enter key student information results in failure of all other functions
0.27 |  | Entry Modification: | User able to return to screen that has already been processed to add optional data
0.28 |  | Cancelation: | Cancelation of an action should be allowed at any time
0.29 |  | Data Restoration: | In the event of a cancelled action all previously entered data should be restored
1 | SignMeUp Framework
1.1 | 1 | Structure: | Provides a structure for the integration of the SignMeUp subsystems
1.2 | 1 | Logon Process: | Manages user logon process
1.3 | 2 | Authorization: | Allows system level authorized users to maintain authorized user information |  |  |  | Note
1.4 | 1 | Menu: | Provides menu for authorized users to access thier project's databases and tools
1.5 | 3 | Print Report: | Allows user to print authorizied user report for whole system or subsystem. Does not contain passwords.
1.6 | 3 | Password Reset: | Allows system-level authorized users to initialize and reset user passwords
2 | Electronic Student Record Subsystem
2.1 | 1 | Structure: | Maintains general student information and course completion info |  |  | Note | Note
2.2 | 3 | Notes: | Notes information shall be maintained in chronological sequence with date, time, id. Never deleted
2.3 | 1 | Print Report: | Possible to print student record. Includes all student info including GPA. Course info optional.
2.4 | 4 | Print Report 2: | Includes info from all universities or current uniniversity
2.5 | 1 | Standards: | Complies with known electronic student record standards.
3 | Course Registration Subsystem
3.1 | 1 | Structure: | Tracks current course offerings, associated schedules, and seats avaibible |  |  |  | Note
3.2 | 2 | Authorization: | Course information maintained by academic department |  |  |  | Faculty page
3.3 | 1 | Restrictions: | Upper div courses required for a major/minor are limited to students with that declared major/minor
3.4 | 1 | Restrictions 2: | Graduate level couses reserved for graduate students
3.5 | 1 | Online Reg: | Allows students to register online for courses for the following semester
3.6 | 1 | One at a Time: | Students may select/register for courses one at a time.
3.7 | 2 | Search Filter: | Students may request list of major courses that meet conditions and register from list. |  |  |  | Note
3.8 | 3 | Schedule Reports: | Generates 3 possible schedule reports. |  | Note
4 | Major Course Requirements Subsystem
4.1 | 1 | Structure: | Track current required courses for all majors and minors |  |  | Note
4.2 | 4 | Structure 2: | Track approved major outlines for each student in each department |  |  | Note
4.3 | 4 | Outline Access: | Outlines created by a major advisor or authorized department user
4.4 | 4 | No Deletion: | Entries can not be deleted from outline once approved.
4.5 | 4 | Modification: | Modification to each element in outline is allowed. History must be maintained
4.6 | 1 | Reports: | Generates 4 possible reports | Note
5 | Faculty and Course Information Subsystem
5.1 | 1 | Structure: | Tracks general faculty info including courses taught by facutly |  |  | Note | Note
5.2 | 1 | Queries: | Database to be queried by following information |  | Note
5.3 | 1 | Query Result: | Queries by faculty name/id return faculty information and list of courses that faculty member can teach
5.4 | 1 | Query Result 2: | Queries by course name/id return course information and list of authorized teachers
5.5 | 1 | Reports: | Generates 4 possible reports | Note
6 | Course Grades Subsystem
6.1 | 1 | Structure: | Allows faculty members to enter and maintain grade info for each course they teach
6.2 | 1 | Display: | Displays list of student names/id and allows faculty member to enter course grade |  |  |  | Note
6.3 | 1 | Notes: | Notes can me made for specific student grade or general notes not for any specific student
6.4 | 3 | Grade Entry: | Grades can only be entered at the end of the current semester unless user has special privlieges
6.5 | 3 | Grade Entry 2: | A user with special update priveleges can update any grade at anytime but their id must be recorded
6.6 | 1 | Printing: | Allows users to print grade sheet. | Note
6.7 | 2 | Reports: | Generates three possible reports | Note

## Project Schedule
CS 532 SE Project Schedule | [6 empty] | Gantt Chart Template © 2020 by Vertex42.com
Course Registration |  |  |  |  | Project Start: | 2022-09-12
Reese Hartwell, Austin Frey, Caleb Greenfield, Maxim Kanayasami, Connor Reid, Mariel Reyes |  |  |  |  | Display Week: | 1 | 2022-09-10 | [6 empty] | 2022-09-17 | [6 empty] | 2022-09-24 | [6 empty] | 2022-10-01 | [6 empty] | 2022-10-08 | [6 empty] | 2022-10-15 | [6 empty] | 2022-10-22 | [6 empty] | 2022-10-29
15 weeks | time axis 2022-09-10 to 2022-11-04
TASK | ASSIGNED | PROGRESS |  | START | DAYS | END | time axis 2022-09-10 to 2022-11-04
Planning |  |  |  | 2022-09-12 | 15 | 2022-09-22
PN 3c: ICSM Common Case | Maxim | 100% |  | 2022-09-12 | 2 | 2022-09-14
PN 3d: Methodologies/techniques | Maxim | 100% |  | 2022-09-12 | 2 | 2022-09-14
PN 4a: Software size and complexity | Reese | 100% |  | 2022-09-12 | 2 | 2022-09-14
PN 4b: Schedule | Caleb | 100% |  | 2022-09-12 | 10 | 2022-09-22
PN 5: Labor hours estimate | All | 100% |  | 2022-09-12 | 2 | 2022-09-14
PN 6: Requirements |  | 100% |  | 2022-09-13 | 9 | 2022-09-22
a: Statement of Scope |  | 100% |  | 2022-09-13 | 9 | 2022-09-22
Functionality and performance descr. | Connor | 100% |  | 2022-09-13 | 6 | 2022-09-19
Use Cases | Austin | 100% |  | 2022-09-20 | 2 | 2022-09-22
b: Requirements analysis | Caleb | 100% |  | 2022-09-13 | 9 | 2022-09-22
PN Deliverable 1 Due | All | 100% |  | 2022-09-12 | 10 | 2022-09-22
Design |  |  |  | 2022-09-23 | 27 | 2022-10-20
Requirements Analysis |  | 100% |  | 2022-09-23 | 7 | 2022-09-30
Database Design |  | 100% |  | 2022-09-29 | 7 | 2022-10-06
Webpage Design |  | 100% |  | 2022-09-29 | 7 | 2022-10-06
Finalize Project Schedule |  | 100% |  | 2022-09-27 | 9 | 2022-10-06
Finalize Duty Assignments |  | 100% |  | 2022-09-27 | 9 | 2022-10-06
Architecture Diagram |  | 100% |  | 2022-10-04 | 7 | 2022-10-11
Detailed Design Description |  | 100% |  | 2022-10-04 | 9 | 2022-10-13
PN Deliverable 2 Due |  | 100% |  | 2022-09-27 | 23 | 2022-10-20
0%
Implementation |  |  |  | 2022-10-07 | 53 | 2022-11-29
Requirements 0.1 - 0.3, 0.11 - 0.12, |  | 100% |  | 2022-10-07 | 4 | 2022-10-11
Requirements 0.19 - 0.20 |  | 100% |  | 2022-10-11 | 3 | 2022-10-14
All Level 1 requirements |  | 100% |  | 2022-10-13 | 7 | 2022-10-20
All Level 2 requirements |  | 90% |  | 2022-10-20 | 12 | 2022-11-01
All Level 3 requirements |  | 90% |  | 2022-10-27 | 12 | 2022-11-08
All Level 4 requirements |  | 80% |  | 2022-11-03 | 12 | 2022-11-15
All Level 5 requirements |  | 85% |  | 2022-11-10 | 12 | 2022-11-22
All Level 6 requirements |  | 75% |  | 2022-11-17 | 12 | 2022-11-29
Finalize Level 0 requirements |  | 90% |  | 2022-11-22 | 7 | 2022-11-29
Finalization |  |  |  | 2022-11-25 | 13 | 2022-12-08
Finalize Subsystem Integration |  | 100% |  | 2022-11-25 | 7 | 2022-12-02
Finalize Presentation |  | 100% |  | 2022-11-29 | 9 | 2022-12-08
-

## Timesheet
Week | Start Date | Name | [5 empty] | *meetings included in individual time
|  | Maxim | Mariel | Reese | Caleb | Austin | Connor
Week 3 | 2022-09-04
Week 4 | 2022-09-11 | 3 | 3 | 3 | 3 | 3 | 2
Week 5 | 2022-09-18 | 2 | 2 | 2 | 2 | 2 | 3
Week 6 | 2022-09-25 | 3 | 3 | 3 | 3 | 3 | 2
Week 7 | 2022-10-02 | 3 | 3 | 3 | 4 | 3 | 2
Week 8 | 2022-10-09 | 4 | 2 | 4 | 5 | 2 | 4
Week 9 | 2022-10-16 | 5 | 2 | 5 | 6 | 2 | 4
Week 10 | 2022-10-23 | 2 | 3 | 4 | 2 | 2 | 3
Week 11 | 2022-10-30 | 2 | 3 | 5 | 3 | 2 | 4
Week 12 | 2022-11-06 | 1 | 2 | 4 | 1 | 2 | 2
Week 13 | 2022-11-13 | 1 | 3 | 3 | 3 | 3 | 2
Week 14 | 2022-11-20 | 3 | 2 | 2 | 3 | 3 | 2
Week 15 | 2022-11-27 | 4 | 5 | 3 | 3 | 3 | 4
Week 16 | 2022-12-04 | 3 | 5 | 4 | 4 | 4 | 2
Member Total (hr): |  | 36 | 38 | 45 | 42 | 34 | 36
Group Total (hr): |  | 231
Formulas:
Start Date = [Start Date, row above]+7